## Release note
Date | Version | update

## Milestone_FCS
Baseline
Education Azul Development Milestone | Education Azul (KS FCS 2026/10/16_M152 release) (VN FCS 2026/10/23) Development : 41WKs |  | Education Azul (KS FCS 2026/9/24_M151 2nd release) (VN FCS 2026/10/2) Development : 38WKs
| MTK8189 |  | MTK8189
ME Development | Start Date | End Date | Start Date | End Date
Kick off | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04
ID Master/Detail Ready | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06
ME design | 2026-01-06 | 2026-02-04 | 2026-01-06 | 2026-02-04
Tooling vendor survey and decision
Tooling vendor decision date
Chinese New Year | 2026-02-14 | 2026-02-22 | 2026-02-14 | 2026-02-22
Mockup drawing release | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-02-13
Mockup ready | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13
Mockup review | 2026-02-25 | 2026-02-26 | 2026-02-25 | 2026-02-26
228 Holidays | 2025-02-27 | 2025-03-01 | 2025-02-27 | 2025-03-01
DFM review | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04
ME drawing modification for tooling | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-06
ME tooling create | 2026-03-07 | 2026-04-17 | 2026-03-07 | 2026-04-17
T1+T2 | 2026-04-18 | 2026-04-25 | 2026-04-18 | 2026-04-25
SI ME parts | 2026-04-26 | 2026-05-12 | 2026-04-26 | 2026-05-12
DB Build | Start Date | End Date | Start Date | End Date
Layout | 2026-01-06 | 2026-02-11 | 2026-01-06 | 2026-02-11
DB Gerber released | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12
PCB FAB | 2026-02-25 | 2026-03-10 | 2026-02-25 | 2026-03-10
DB SMT Build | 2026-03-11 | 2026-03-15 | 2026-03-11 | 2026-03-15
Ship DB PCBA ETA to TPE RD & HP | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23
DB SVTP test | 2026-03-23 | 2026-04-26 | 2026-03-23 | 2026-04-26
Google validation | 2026-03-23 | 2026-04-26 | 2026-03-23 | 2026-04-26
Labor Holiday | 2025-05-01 | 2025-05-03 | 2025-05-01 | 2025-05-03
DB exit | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23
SI Phase | Start Date | End Date | Start Date | End Date
SI Gerber release | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27
PCB FAB | 2026-04-27 | 2026-05-11 | 2026-04-27 | 2026-05-11
SI SMT build | 2026-05-12 | 2026-05-24 | 2026-05-12 | 2026-05-24
SI Pre-Build | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15
SI Main build | 2026-05-19 | 2026-05-20 | 2026-05-19 | 2026-05-20
OOBIP |  |  | 2026-05-20 | 2026-05-27
Ship SI unit ETA to NSDD (PCBA Only) | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22
Ship SI unit ETA to QAD/TPE RD & HP | 2026-05-28 | 2026-05-28 | 2026-05-27 | 2026-05-27
SI SVTP test | 2026-05-28 | 2026-06-24 | 2026-05-28 | 2026-06-24
Google dogfooding | 2026-05-28 | 2026-06-24 | 2026-05-28 | 2026-06-24
Dragon Festival | 2026-06-19 | 2026-06-21 | 2026-06-19 | 2026-06-21
SI exit | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-02
PV Phase | Start Date | End Date | Start Date | End Date
PV Gerber release | 2026-06-24 | 2026-06-24 | 2026-06-18 | 2026-06-18
PCB FAB | 2026-06-24 | 2026-07-08 | 2026-06-19 | 2026-07-06
PV SMT Build | 2026-07-09 | 2026-07-12 | 2026-07-07 | 2026-07-10
VN SMT build | 2026-07-27 | 2026-07-28 | 2026-07-21 | 2026-07-22
PV Pre-Build | 2026-07-13 | 2026-07-13 | 2026-07-10 | 2026-07-10
VN Pre-build | 2026-08-01 | 2026-08-01 | 2026-07-27 | 2026-07-27
PV Main build | 2026-07-16 | 2026-07-17 | 2026-07-14 | 2026-07-15
VN Main-build | 2026-08-05 | 2026-08-06 | 2026-07-29 | 2026-07-29
OOBIP |  |  | 2026-07-11 | 2026-07-31
Ship PV unit ETA to NSDD (PCBA Only) | 2026-07-20 | 2026-07-20 | 2026-07-15 | 2026-07-15
Ship PV unit ETA to QAD/TPE RD & HP | 2026-07-24 | 2026-07-24 | 2026-07-22 | 2026-07-22
PV SVTP test | 2026-07-24 | 2026-08-31 | 2026-07-23 | 2026-08-19
Google dogfooding | 2026-07-24 | 2026-08-31 | 2026-07-23 | 2026-08-19
Product lock down
Code Freeze(FSI candidate) | 2026-09-11 | 2026-09-11 | 2026-08-28 | 2026-08-28
PV Regression | 2026-09-12 | 2026-09-17 | 2026-08-31 | 2026-09-03
RTM Ties-1 | 2026-09-18 | 2026-09-18 | 2026-09-04 | 2026-09-04
PV exit | 2026-09-11 | 2026-09-11 | 2026-09-03 | 2026-09-03
ME PV-R- KS | Start Date | End Date | Start Date | End Date
PV-R build (use PV MB) w/o R/I, SWDL, OBE | 2026-08-26 | 2026-08-26 | 2026-08-17 | 2026-08-17
By part | 2026-08-31 | 2026-09-03 | 2026-08-21 | 2026-08-25
Tooling lock down | 2026-09-03 | 2026-09-03 | 2026-08-25 | 2026-08-25
ME PV-R- VN | Start Date | End Date | Start Date | End Date
PV-R build (use PV MB) w/o R/I, SWDL, OBE | 2026-08-26 | 2026-08-26 | 2026-08-27 | 2026-08-27
Tooling lock down | 2026-09-03 | 2026-09-03 | 2026-09-02 | 2026-09-02
VN SMT build | 2026-09-28 | 2026-09-30 | 2026-09-11 | 2026-09-13
MV Pre-Build | 2026-09-21 | 2026-09-21 | 2026-09-05 | 2026-09-05
VN Pre-build | 2026-10-06 | 2026-10-06 | 2026-09-15 | 2026-09-15
MV Main build | 2026-09-23 | 2026-09-24 | 2026-09-08 | 2026-09-13
VN Main-build | 2026-10-08 | 2026-10-09 | 2026-09-17 | 2026-09-17
MV iFOOBA | 2026-09-24 | 2026-09-26 | 2026-09-13 | 2026-09-15
Marketing OOBA | 2026-09-28 | 2026-09-30 | 2026-09-15 | 2026-09-17
Mini Regression -1 | 2026-10-06 | 2026-10-08 | 2026-09-14 | 2026-09-16
Mini Regression -2
Product release-KS | 2026-10-08 | 2026-10-08 | 2026-09-17 | 2026-09-17
Product release-VN | 2026-10-15 | 2026-10-15 | 2026-09-24 | 2026-09-24
National Holiday | 2025-10-09 | 2025-10-11
First Order Drop | 2026-10-09 | 2026-10-09 | 2026-09-17 | 2026-09-17
KS FCS | 2026-10-16 | 2026-10-16 | 2026-09-24 | 2026-09-24
VN FCS | 2026-10-23 | 2026-10-23 | 2026-10-02 | 2026-10-02
Condition | 1. Google/MTK kickoff : 1/23 2. Go with M152
Formulas:
Start Date = [End Date, row above]+2
End Date = [Start Date]+2

## MTK-FCS0924
X
|  |  |  | w02 | [6 empty] | w03 | [6 empty] | w04 | [6 empty] | w05 | [6 empty] | w06 | [6 empty] | w07 | [6 empty] | w08 | [6 empty] | w09 | [6 empty] | w10 | [6 empty] | w11 | [6 empty] | w12 | [6 empty] | w13 | [6 empty] | w14 | [6 empty] | w15 | [6 empty] | w16 | [6 empty] | w17 | [6 empty] | w18 | [6 empty] | w19 | [6 empty] | w20 | [6 empty] | w21 | [6 empty] | w22 | [6 empty] | w23 | [6 empty] | w24 | [6 empty] | w25 | [6 empty] | w26 | [6 empty] | w27 | [6 empty] | w28 | [6 empty] | w29 | [6 empty] | w30 | [6 empty] | w31 | [6 empty] | w32 | [6 empty] | w33 | [6 empty] | w34 | [6 empty] | w35 | [6 empty] | w36 | [6 empty] | w37 | [6 empty] | w38 | [6 empty] | w39 | [6 empty] | w40 | [6 empty] | w41 | [6 empty] | w42 | [6 empty] | w43 | [6 empty] | w44 | [6 empty] | w45 | [6 empty] | w46 | [6 empty] | w47 | [6 empty] | w48 | [6 empty] | w49 | [6 empty] | w50 | [6 empty] | w51 | [6 empty] | w52
 | time axis 2026-01-04 to 2026-12-26
 | time axis 2026-01-04 to 2026-12-26
Intel CPU | bar: 2026-09-18
dashboard | MTK8189
dashboard | Google-M151 |  |  | 2026-06-15: Feature Freeze; 2026-07-14: Beta Promotion; 2026-08-11: Stable release; 2026-08-25: 2nd Stable release; 2026-08-29: 2nd FSI candidate; 2026-09-04: FSI signoff
[82 empty] | BVT | [63 empty] | BVT | [55 empty] | BVT | [6 empty] | Bug cutoff | [6 empty] | FW cutoff | [6 empty] | OS cutoff
[23 empty] | MTK/Google review | [58 empty] | FAFT | [63 empty] | FAFT | [55 empty] | FAFT
|  | PCB:2-2-2 | SMT |  |  | Layout | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | G-eMMC |  |  | G-UFS | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | DB SMT | [42 empty] | Phase exit |  |  |  | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | SI SMT | [36 empty] | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | PV SMT | [40 empty] | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | MV SMT | [21 empty] | FCS
|  |  | FATP |  |  |  | MTK/Google review 29: Award | [31 empty] | Bright-up | [63 empty] | SI Pre build |  |  |  |  | SI Main build | [42 empty] | Phase exit | [6 empty] | SOP |  | PV Pre build |  |  |  | PV Main build | [32 empty] | PV-R |  |  |  | TLD | TLD |  | TLD | TLD | [8 empty] | Phase exit |  | MV FAI |  |  | MV Main & FOOBA
|  |  | SVTP Test & NSDD Test | [78 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | [31 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [28 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [28 empty] | PR
|  |  | MTV and Google validation | [78 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | [31 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [28 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [25 empty] | MV-R
|  |  | ME | [128 empty] | ME ETA |  | SOP build | [54 empty] | ME ETA |  |  |  |  | ME critical | [32 empty] | ME ETA | [20 empty] | ME ETA
|  |  | VN SMT | [198 empty] | SMT | [51 empty] | SMT | [12 empty] | PR | [7 empty] | FCS
|  |  | VN FATP | [204 empty] | Pre-build |  | Main-build | [28 empty] | PV-R | [5 empty] | TLD | [12 empty] | Pre-build |  | Main-build & FOOBA
ME | ID/ME
| ME design |  |  |  |  | ME design | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Tooling Vendor
Mockup
| create | [34 empty] | Mock-up build | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| review | [54 empty] | MU review
Tooling
| DFM review | [59 empty] | DFM
| modification | [61 empty] | EC
| release | [64 empty] | S
| create | [64 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
| T1 & T2 | [106 empty] | T1 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| SI ME parts development | [114 empty] | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
| PV ME parts development | [171 empty] | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
| PV-R ME parts development | [212 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| MV ME parts development | [232 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## MTK-FCS1016-A
X
|  |  |  | w02 | [6 empty] | w03 | [6 empty] | w04 | [6 empty] | w05 | [6 empty] | w06 | [6 empty] | w07 | [6 empty] | w08 | [6 empty] | w09 | [6 empty] | w10 | [6 empty] | w11 | [6 empty] | w12 | [6 empty] | w13 | [6 empty] | w14 | [6 empty] | w15 | [6 empty] | w16 | [6 empty] | w17 | [6 empty] | w18 | [6 empty] | w19 | [6 empty] | w20 | [6 empty] | w21 | [6 empty] | w22 | [6 empty] | w23 | [6 empty] | w24 | [6 empty] | w25 | [6 empty] | w26 | [6 empty] | w27 | [6 empty] | w28 | [6 empty] | w29 | [6 empty] | w30 | [6 empty] | w31 | [6 empty] | w32 | [6 empty] | w33 | [6 empty] | w34 | [6 empty] | w35 | [6 empty] | w36 | [6 empty] | w37 | [6 empty] | w38 | [6 empty] | w39 | [6 empty] | w40 | [6 empty] | w41 | [6 empty] | w42 | [6 empty] | w43 | [6 empty] | w44 | [6 empty] | w45 | [6 empty] | w46 | [6 empty] | w47 | [6 empty] | w48 | [6 empty] | w49 | [6 empty] | w50 | [6 empty] | w51 | [6 empty] | w52
 | time axis 2026-01-04 to 2026-12-26
 | time axis 2026-01-04 to 2026-12-26
Intel CPU | bar: 2026-09-18
dashboard | MTK8189
dashboard | Google-M152 |  |  | 2026-07-13: Feature Freeze; 2026-08-11: Beta Promotion; 2026-09-08: Stable release; 2026-09-11: FSI candidate; 2026-09-18: FSI signoff
[82 empty] | BVT | [65 empty] | BVT | [56 empty] | BVT | [10 empty] | SW cutoff | [6 empty] | OS cutoff | [6 empty] | FW candiate | [6 empty] | FW lockdown
[23 empty] | MTK/Google review | [58 empty] | FAFT | [65 empty] | FAFT | [56 empty] | FAFT
|  | PCB:2-2-2 | SMT |  |  | Layout | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | G-eMMC |  |  | G-UFS | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | DB SMT | [42 empty] | Phase exit |  |  |  | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | SI SMT | [42 empty] | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | PV SMT | [52 empty] | G | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | MV SMT | [29 empty] | FCS
|  |  | FATP |  |  |  | MTK/Google review 29: Award | [31 empty] | Bright-up | [63 empty] | SI Pre build |  |  |  |  | SI Main build | [42 empty] | Phase exit | [10 empty] | PV Pre build |  |  |  | PV Main build | [39 empty] | PV-R |  |  |  |  | TLD | TLD | TLD | TLD | [7 empty] | Phase exit | [9 empty] | MV FAI |  | MV Main
|  |  | SVTP Test & NSDD Test | [78 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | [31 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [29 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | [37 empty] | PR
|  |  | MTV and Google validation | [78 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | [31 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [29 empty] | Google doogfooding(28) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | [35 empty] | MV-R
|  |  | ME | [128 empty] | ME ETA |  | SOP build | [56 empty] | ME ETA | [14 empty] | 33 33: ME ETA | [17 empty] | ME ETA
|  |  | VN SMT | [202 empty] | 4 4: SMT | [27 empty] | SMT | [16 empty] | PR | [7 empty] | FCS
|  |  | VN FATP | [202 empty] | 7 7: SOP build; 9 9: Pre-build; 13 13: Main-build | [6 empty] | PV-R |  |  |  | TLD | [24 empty] | Pre-build |  | Main-build
ME | ID/ME
| ME design |  |  |  |  | ME design | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Tooling Vendor
Mockup
| create | [34 empty] | Mock-up build | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| review | [54 empty] | MU review
Tooling
| DFM review | [59 empty] | DFM
| modification | [61 empty] | EC
| release | [64 empty] | S
| create | [64 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
| T1 & T2 | [106 empty] | T1 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| SI ME parts development | [114 empty] | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
| PV ME parts development | [172 empty] | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
| PV-R ME parts development | [221 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| MV ME parts development | [244 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16

## Gantt 428 (hidden)
[8 empty] | 6/3 Dragon Boat (TW/CN) | [100 empty] | Mid-Autumn 9/12 | [18 empty] | 10/1-5 National (KS) | [20 empty] | 10/9-11 National (TW) | [69 empty] | 12/31-1/2 New Year | [43 empty] | 1/31 CNY Eve | [14 empty] | 228假期 | [33 empty] | 清明
|  |  | w23 | [6 empty] | w24 | [6 empty] | w25 | [6 empty] | w26 | [6 empty] | w27 | [6 empty] | w28 | [6 empty] | w29 | [6 empty] | w30 | [6 empty] | w31 | [6 empty] | w32 | [6 empty] | w33 | [6 empty] | w34 | [6 empty] | w35 | [6 empty] | w36 | [6 empty] | w37 | [6 empty] | w38 | [6 empty] | w39 | [6 empty] | w40 | [6 empty] | w41 | [6 empty] | w42 | [6 empty] | w43 | [6 empty] | w44 | [6 empty] | w45 | [6 empty] | w46 | [6 empty] | w47 | [6 empty] | w48 | [6 empty] | w49 | [6 empty] | w50 | [6 empty] | w51 | [6 empty] | w52 | [6 empty] | w53 | [6 empty] | w1 | [6 empty] | w2 | [6 empty] | w3 | [6 empty] | w4 | [6 empty] | w5 | [6 empty] | w6 | [6 empty] | w7 | [6 empty] | w8 | [6 empty] | w9 | [6 empty] | w10 | [6 empty] | w11 | [6 empty] | w12 | [6 empty] | w13 | [6 empty] | w14 | [6 empty] | w15 | [6 empty] | w16 | [6 empty] | w17
 | time axis 2021-05-29 to 2022-04-30
 | time axis 2021-05-29 to 2022-04-30
16 | 2022 Envy16 CS (FCS 2022/4/8) | SMT | [32 empty] | Layout | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | [8 empty] | ES Sample |  |  | DB SMT | [7 empty] | Ship | [33 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | QS Sample | 12 | 13 | 14 | SI SMT | [42 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | [5 empty] | PV SMT | [51 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | [9 empty] | MV SMT
|  | FATP | [8 empty] | Award | [153 empty] | SI pre-build |  | SI FAI |  | SI Main | [6 empty] | Ship | [39 empty] | Inventory Check | [11 empty] | PV pre-build |  | PV FAI |  | PV Main | [5 empty] | Ship | [67 empty] | MV FAI |  | MV Main | [10 empty] | MVR-1 | [6 empty] | MVR-2 |  |  |  | PR | [6 empty] | FCS
|  | Test | [107 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | [7 empty] | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [30 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [35 empty] | T | 2 | [9 empty] | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | PLD | [6 empty] | CFZ |  |  | PV-R |  |  |  | RTM
|  | ME | [135 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | SI parts ETA | [43 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | PV parts ETA | [34 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | PV-R | DQA | Cos | TLD | TLD | TLD | TLD | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  | VC | [56 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | ETA | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | [5 empty] | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | ETA | [16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | ETA | [24 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [9 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | ETA
[148 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | SI2 SMT for CPU AUX power (MPS MP2961) + IR sensor
[174 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Elan TS SMT |  | ETD |  |  | ETA | Elan FW tuning
ME | ID/ME | [10 empty] | ID/ME | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | [154 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
| ME design | [19 empty] | ME design | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Tooling Vendor | [26 empty] | Tooling vendor survey & decision | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | vendor lock down
| Mockup | [27 empty] | 25 18: mockup; 26 19: drawing release
| create | [44 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| review | [52 empty] | review | 2 | 3 | 4
ACD parts Tooling (AL)
| DFM review | [44 empty] | drawing release 4: Tooling (Al) | DFM | 2 | 3 | 4 | 5 | 6
| modification | [58 empty] | modification | modification | 3
| release | [61 empty] | drawing release
| create | [61 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
| T0 & T2 | [102 empty] | T2 | bar: drawing release 35
Plastic parts Tooling
| DFM review | [54 empty] | Tooling (plastic) |  |  |  | DFM
| modification | [59 empty] | modification | bar: drawing release 1
| release | [61 empty] | drawing release 2: drawing release
| create | [62 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| T0 & T2 | [93 empty] | T2 | bar: drawing release 25
| SI ME parts development | [103 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Intel CPU
| RPL-U 282 15w | [90 empty] | ES ww35 | [55 empty] | ES ww43 | [48 empty] | Prod ww50
ES2 ww21-22

## Gantt 317 (hidden)
[8 empty] | 6/3 Dragon Boat (TW/CN) | [100 empty] | Mid-Autumn 9/12 | [18 empty] | 10/1-5 National (KS) | [20 empty] | 10/9-11 National (TW) | [69 empty] | 12/31-1/2 New Year | [43 empty] | 1/31 CNY Eve | [14 empty] | 228假期 | [33 empty] | 清明
|  |  | w23 | [6 empty] | w24 | [6 empty] | w25 | [6 empty] | w26 | [6 empty] | w27 | [6 empty] | w28 | [6 empty] | w29 | [6 empty] | w30 | [6 empty] | w31 | [6 empty] | w32 | [6 empty] | w33 | [6 empty] | w34 | [6 empty] | w35 | [6 empty] | w36 | [6 empty] | w37 | [6 empty] | w38 | [6 empty] | w39 | [6 empty] | w40 | [6 empty] | w41 | [6 empty] | w42 | [6 empty] | w43 | [6 empty] | w44 | [6 empty] | w45 | [6 empty] | w46 | [6 empty] | w47 | [6 empty] | w48 | [6 empty] | w49 | [6 empty] | w50 | [6 empty] | w51 | [6 empty] | w52 | [6 empty] | w53 | [6 empty] | w1 | [6 empty] | w2 | [6 empty] | w3 | [6 empty] | w4 | [6 empty] | w5 | [6 empty] | w6 | [6 empty] | w7 | [6 empty] | w8 | [6 empty] | w9 | [6 empty] | w10 | [6 empty] | w11 | [6 empty] | w12 | [6 empty] | w13 | [6 empty] | w14 | [6 empty] | w15 | [6 empty] | w16 | [6 empty] | w17
 | time axis 2021-05-29 to 2022-04-30
 | time axis 2021-05-29 to 2022-04-30
16 | 2022 Envy16 CS (FCS 2022/4/8) | SMT | [31 empty] | Layout | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | ES Sample |  | DB SMT | [6 empty] | Ship | [23 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | [5 empty] | 12 | 13 | 14 |  | SI SMT | [17 empty] | QS Sample | [23 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | PV SMT | [21 empty] | Inventory Check | [22 empty] | G | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | MV SMT | [10 empty] | RTS
|  | FATP | [8 empty] | Award | [129 empty] | SI pre-build |  |  | SI FAI |  | SI Main | [6 empty] | Ship | [46 empty] | PV pre-build |  | PV FAI |  | PV Main | [6 empty] | Ship | [55 empty] | MV FAI |  |  | MV Main | [6 empty] | MVR-1 | [6 empty] | MVR-2 |  |  |  | PR | [6 empty] | FCS
|  | Test | [87 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [34 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | [31 empty] | T | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | PLD | [13 empty] | CFZ |  |  | PV-R |  |  |  | RTM
|  | ME | [112 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [5 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | SI parts ETA | [34 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | PV parts ETA | [13 empty] | S | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | PV-R | DQA | DQA | TLD | TLD | TLD | TLD | 1 | 2 | 3 | [9 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  | VC | [56 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | ETA | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | [5 empty] | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | ETA | [16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | ETA | [24 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [9 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | ETA
[148 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | SI2 SMT for CPU AUX power (MPS MP2961) + IR sensor
[174 empty] | G | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Elan TS SMT |  | ETD |  |  | ETA | Elan FW tuning
ME | ID/ME | [10 empty] | ID/ME | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | [154 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
| ME design | [19 empty] | ME design | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Tooling Vendor | [26 empty] | Tooling vendor survey & decision | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | vendor lock down
| Mockup | [27 empty] | 25 18: mockup; 26 19: drawing release
| create | [44 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| review | [52 empty] | review | 2 | 3 | 4
ACD parts Tooling (AL)
| DFM review | [44 empty] | drawing release 4: Tooling (Al) | DFM | 2 | 3 | 4 | 5 | 6
| modification | [58 empty] | modification | modification | 3
| release | [61 empty] | drawing release
| create | [61 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
| T0 & T2 | [102 empty] | T2 | bar: drawing release 35
Plastic parts Tooling
| DFM review | [54 empty] | Tooling (plastic) |  |  |  | DFM
| modification | [59 empty] | modification | bar: drawing release 1
| release | [61 empty] | drawing release 2: drawing release
| create | [62 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| T0 & T2 | [93 empty] | T2 | bar: drawing release 25
| SI ME parts development | [103 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Intel CPU
| RPL-U 282 15w | [90 empty] | ES ww35 | [55 empty] | QS ww43 | [48 empty] | Prod ww50 | [69 empty] | RTS ww07
| RPL-P 682 28w | [54 empty] | ES ww30 | [48 empty] | 9: QS ww38 | [36 empty] | Prod ww45 | [62 empty] | RTS ww01
| RPL-H 682 45w | [54 empty] | ES ww30 | [48 empty] | 9: QS ww38 | [22 empty] | Prod ww43 | [55 empty] | RTS ww51
1.Compal travel support : Yes
2. ME Design 30 days
3. 10 layer PCB, non-HDI
4. Layhout 35 days 需EE確認
5. ME L/T 21 days
6. A/C/D Tooling create 35 days
7. KS DQA own MVR (No Shipping
8. TLD備料時間不足 PV sample/SI unit for test
9. SI w/ ES sample
10. ES sample需要8/17到
11. TPE ME SAMPLE & 備料同步